Evaluation Report Title: / Trade in Global Value Chains Initiative: Final Evaluation Report

Response to Evaluation Report (overarching narrative)
The Trade in Global Value Chains Initiative (TGVCI) was a programme working in Kenya, South Africa and Bangladesh to support resilient supply chains in the horticulture and garment sectors. It was a modified challenge fund, using matched funding to support 20 projects with coalitions of private sector firms, NGOs and civil society. / We welcome this evaluation, completed by the Natural Resources Institute, which will be used to inform our lessons learned and inform future DFID work in this area. / The DFID funded research programme ‘Capturing the Gains’ suggested that an improvement in the quality of jobs, and employment and social conditions for workers and farmers (termed as Social Upgrading) is required for better productivity and increased value addition (Economic Upgrading) for firms in the longer term. TGVCI was therefore a pilot that sought specifically to test what type of value chain interventions would be most effective in achieving economic and social upgrading in GVCs. / TGVCI projects led to improvements in workers’ skills (technical skills, life skills and leadership skills), workers health and nutrition, ethical compliance and engagement with smallholders. Overall, it directly benefited more than 100,000 people and indirectly benefitted over a million people working in export-oriented farms, agro-processing centres and factories in Kenya, South Africa and Bangladesh. Many of the projects have been extended and expanded since the TGVCI programme finished, demonstrating that firms and others participating in the programme are convinced of the value of investing in social upgrading as a good business model. / Overall, the evaluation gives a ‘moderate’ score for the programme given that, although there was effective social upgrading, bringing benefits to workers, there was little evidence on the linkage to direct business benefits. There were limitations in the ability to collect sufficient project monitoring data and given a large number of different projects with varying methods, and this makes it hard to make overarching conclusions on economic upgrading. / This evaluation has provided valuable information to inform DFID’s work; both in terms of programmes that aim to achieve similar impacts, and for wider lessons learned on running catalytic funds or modified challenge funds and partnering with the private sector. DFID is not running another phase of the Trade in Global Value Chains Initiative, but it is continuing to work in social upgrading in supply chains, responsible business and private sector development. The findings of this evaluation (including the Mid Term Evaluation Report) have already been used to inform programme decisions in these areas, and this final evaluation report will be disseminated within DFID to inform future programming decisions.

Evaluation Report Title: Trade in Global Value Chains Initiative: Final Evaluation Report

Recommendations	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
N/A. Given the programme has ended and there is not a direct follow-up, the Report provides lessons for future work rather than direct recommendations for the programme.